Parara USA Inc.

Title:	2014-2016 Committee Vision and 1st year Objectives

Sponsor:		Parara Executive Committee

Purpose:	Describe the vision and 1st year goals of Parara USA created by 2014-2016 office

Who:			The procedure applies to all executives

Vision

Build a sustainable agricultural and educational institute in Juba, South Sudan that will help local community and Parara USA in 8-10 years.

What are the benefits of Agricultural and Educational institute?

- Educate local farmers of agricultural know how and best practices and educate public of benefits of buying locally produced food.

- Support local farmers by providing them with tools and access to market.

- Unite local farmers and community

Road Map: How to make our vision a reality?

Core Strategy

- Improve local organization in USA

- Ally/partner with other organizations in USA and Juba, South Sudan

- Establish a local office in Juba and build strong relationship with BC-Juba

1st Year objectives

| # | Action | Cost estimate | 1st progress check |
| --- | --- | --- | --- |
| 1 | Complete 501-c3 application | $ 500-2,000 | 9/6/14 |
| 2 | Register all Parara land/assets in Juba | 2,000 | 10/1/14 |
| 3 | Build a fence on all properties in Juba | 1,000 | xx |
| 4 | Good online presence and cultural education | ? | 9/6/14 |
| 5 | Momoret 2015 | $10,000 | 8/24/14 |
| 6 | Establish emergency fund | $4,000 | 10/1/14 |
| 7 | Continue Parara scholarship | $2,000 | 10/1/14 |
|  | Total | ~11500 |  |

2nd Year Objectives

| # | Action | Cost estimate | 1st progress check |
| --- | --- | --- | --- |

Ask members to donate 25$, $50, 100$